## AIDECK Dev Tracker
Row | Task | Files | Status | Last Update
1 | Foundation & MVP Core
1.1 | Set up FastAPI backend and async PostgreSQL |  | ❌ Not started
1.2 | Implement JWT-based authentication |  | ❌ Not started
1.3 | Define RBAC roles in `models.py` |  | ❌ Not started
1.4 | Create Docker + Docker Compose setup |  | ❌ Not started
1.5 | Scaffold React frontend app |  | ❌ Not started
2 | Secure Auth & Token Tracking
2.1 | Integrate OAuth2 provider |  | ❌ Not started
2.2 | Add rate-limiting via FastAPI-Limiter |  | ❌ Not started
2.3 | Implement token and role-based permissions |  | ❌ Not started
2.4 | Initialize token tracking (OpenAI usage) |  | ❌ Not started
3 | Agent System
3.1 | Create BaseAgent class with Pydantic I/O |  | ❌ Not started
3.2 | Add Planner, ProgressTracker, BugHunter agents |  | ❌ Not started
3.3 | Log all agent output in `agent_logs.py` |  | ❌ Not started
3.4 | Create AgentFactory |  | ❌ Not started
4 | AI Orchestration + Vector Store Abstraction
4.1 | Implement `orchestrator.py` for inter-agent workflows |  | ❌ Not started
4.2 | Add Celery + Redis for background task execution |  | ❌ Not started
4.3 | Abstract VectorStore into switchable backend (ChromaDB, Pinecone) |  | ❌ Not started
4.4 | Define standard agent state transitions |  | ❌ Not started
5 | RAG & Embeddings
5.1 | Configure embedding logic in `vector_tools.py` |  | ❌ Not started
5.2 | Store project vectors in ChromaDB |  | ❌ Not started
5.3 | Enable RAG-based BugHunter functionality |  | ❌ Not started
5.4 | Link embeddings to per-project IDs |  | ❌ Not started
6 | Frontend UI & State Management
6.1 | Build AgentDashboard, PlanView, LogsPage |  | ❌ Not started
6.2 | Use Zustand or Redux Toolkit to manage agent states |  | ❌ Not started
6.3 | Integrate React Query for API call caching |  | ❌ Not started
6.4 | Display AI results + logs visually |  | ❌ Not started
7 | Testing, Monitoring, Docs
7.1 | Write tests (Pytest for backend, Jest/Cypress for frontend) |  | ❌ Not started
7.2 | Load test orchestration with Locust |  | ❌ Not started
7.3 | Add Prometheus + Grafana dashboard |  | ❌ Not started
7.4 | Enable Sentry error tracking |  | ❌ Not started
7.5 | Auto-generate OpenAPI docs |  | ❌ Not started
7.6 | Maintain ADRs in `docs/decisions/` |  | ❌ Not started